## Sheet1
Employee name | Rank and Grade | Bench Category Column | 6 Weeks Forecast | 12 Weeks Forecast | Current Week Forecast | WC 7 Jul 2026 | WC 14 Jul 2026 | WC 22 Jul 2026 | WC 29 Jul 2026 | WC 5 Aug 2026 | WC 12 Aug 2026 | WC 19 Aug 2026 | Allocation | % availability for next 6 months | End date | Nationality | Previous/Existing Project Roles | Primary Skillset (Platform) | Secondary Skillset | Aspiring roles | Current Engagement | EM | Updated? | For FY26 (Jul 2025 to Jun 2026), were you 100% fulfilled on a project? | If you were NOT 100% for FY26 (Jul 2025 to Jun 2026), why not? | What are your planned activities after your current engagement ends, if it is expected to conclude within the next six months? | MS FORM DONE?
Doe, Jamie JD | Associate 1 | Coming on bench in 4 week(s) | 50% | 75% | 100% | 100% | 75% | 50% | 50% | 0% | 0% | 0% | Jul - Sep 2026 - Dummy Project Alpha 50% | 80% | 2026-09-30 | Fictional | Business Analyst | Python, SQL, Excel, Power BI | Cloud Fundamentals | Data / AI Consultant | Dummy Client - Project Alpha Implementation - E-00000001 | Manager, Alex | yes | Yes | N/A | Training, knowledge transfer, and internal BD activities | yes
[13 empty] | Oct - Dec 2026 - Dummy Project Beta 50% | [5 empty] | Power BI, Data Visualization, Stakeholder Management | Solution Consultant
Internal enablement until next assignment
Tan, Morgan MT | Senior 2 | Coming on bench in 12 week(s) | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 75% | 75% | 50% | Jan 2027 - Dummy Project Gamma | 100% | 2026-12-31 | Fictional | Data Engineer | Terraform, Python, SQL, Scripting | GenAI Engineering | Cloud Engineer / GenAI Engineer | Dummy Agency - Maintenance Phase 1 and 2 - E-00000002 | Manager, Blair | yes | Yes | N/A | Continue support activities and prepare handover notes | yes
[13 empty] | Jul - Dec 2026 - Dummy Maintenance 100% | [6 empty] | GenAI Engineering
Jan - Jun 2027 - Dummy Support 100%